## Sheet1
Task | Deliverables | Who? | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Design work
- Screens and responsive layout | .psd files | Ben | bar: 27; 29
- User story | Word Doc | Ben | bar: 27; 29
- Psuedo coding | Word Doc | Udara | bar: 29
- Explore Zepplin or InvisionApp | TBC | Ben | bar: 30
Project Management
- GitHub management | See ... best practice | Ana/Udara | bar: 27 to 28
Documentation
- GitHub best practice | One page operating manual | Ana/Udara | bar: 29
Front end
- Quick wireframes | Wireframe page layouts with HTML tag info | Ben | bar: 29
- Create simple Bootstrap front end with pagination | Inline CSS and custom CSS files | Ben | bar: 1 to 2
- Additional page views | TBC | ?
- Add a product to cart | Sessions or cookies - code for storing user choice | Nathan
- Remove product to cart | Code | Nathan
- Go to check out page to get a detailed view of the cart | Code | Nathan
Back end
- Define data fields | List of fields | All | bar: 27
- Create seed content | Data and images | Nathan/Ben | bar: 28
- Set up file structure | Set up environment | Andy | bar: 27
- Write app.js and routes | Code | Andy | bar: 27; 30
- Create database | DB | Udara
- Create tables/model | DB | Udara
- populate db with a seed file | Data | Udara
- code controller ORM sequelize | Code | Ben/Ana | bar: 28
- Write the Handlebars logic for outputting HTML | Code | Ana | bar: 31